## How to use
Apparel Production Calendar Template
apparelconsulting.us
What this is
A backward-planned production calendar. Enter your launch date and the duration of each stage; every milestone date calculates itself.
Why backward
Forward planning produces optimism — you start at today, add what each step should take, and arrive at a date that assumes nothing goes wrong. Backward planning from a fixed launch date gives you the dates things must happen by, and immediate visibility when one slips.
How to use it
• | Set the launch date in the yellow cell on Calendar.
• | Adjust the duration of each stage for your product and sourcing region. Defaults are domestic; the Benchmarks sheet has overseas figures.
• | Dates calculate backwards from launch. If the earliest start is in the past, your launch date is not achievable — change the date or the plan.
• | Update Actual dates weekly. Variance shows the moment something slips.
The one milestone that matters most
Fabric in-house. Almost every late delivery traces back to fabric arriving later than assumed, and it slips quietly — weeks before anyone notices production start has moved with it. Confirm it in writing, chase it weekly, escalate the day it moves.
Buffers that survive contact with reality
• | One extra sample round beyond what you think you need
• | Two weeks between goods received and launch, for photography and 3PL intake
• | A week either side of any customs clearance
• | Chinese New Year: overseas production stops for weeks, with a slow ramp either side
Free to use and adapt. Built by Apparel Consulting — apparelconsulting.us

## Calendar
Production Calendar
Enter the launch date; everything else plans backwards
Launch date |  | <- enter your launch date here
# | Milestone | Weeks needed | Must happen by | Actual | Variance (days) | Notes
1 | Launch | 0 |  |  |  | Fixed point. Everything plans backwards from here.
2 | Goods received at warehouse / 3PL | 2 |  |  |  | Photography, intake, QC on receipt
3 | Shipment released / inspection passed | 1 |  |  |  | Balance payment tied to this
4 | Bulk production complete | 1
5 | Bulk production start | 5 |  |  |  | 20-35 days typical for a straightforward garment
6 | Fabric and trims in-house at factory | 2 |  |  |  | THE critical milestone — track it weekly
7 | Fabric and trim orders placed | 6 |  |  |  | Custom-dyed is weeks; stock fabric is days
8 | PP sample approved and sealed | 2 |  |  |  | Bulk must not be cut before this exists
9 | Fit sample approved | 3 |  |  |  | Measured against spec; grade reviewed
10 | Proto sample approved | 3
11 | Tech pack and pattern complete | 3 |  |  |  | Nothing can be quoted or sampled without it
12 | Factory confirmed and PO issued | 2 |  |  |  | Confirmed capacity, not a verbal hold
13 | Product definition complete | 2 |  |  |  | Category, construction, fabric, quantities, target cost
| Earliest start required |  |  |  |  | If this date is in the past, the launch date is not achievable.
Total weeks required
Durations run in sequence here, which is deliberately conservative. Sourcing and tech pack work can overlap, and fabric ordering should start alongside sampling rather than after it — but plan the conservative version first and compress knowingly, not by accident.

## Benchmarks
Stage Benchmarks
Typical ranges — adjust for your product
Stage | Domestic (LA) | Overseas | Notes
Product definition | 1-4 weeks | 1-4 weeks | Same either way; this is your work, not the factory's
Tech pack + pattern | 2-4 weeks | 2-4 weeks | Nothing can be quoted or sampled before this
Sourcing + quoting | 2-4 weeks | 3-6 weeks | Overlaps with sampling if you are organised
Per sample round | 2-3 weeks | 3-5 weeks | Overseas adds shipping both ways on every round
Total sampling (3-4 rounds) | 6-12 weeks | 12-20 weeks | The stage that expands; vague comments are why
Fabric lead time | Days (stock) to 6 weeks | 4-10 weeks | The most common cause of a blown calendar
Bulk production | 3-6 weeks | 4-8 weeks | 20-35 days typical after approval and fabric
Inspection | 2-5 days | 1-2 weeks | Book it in advance, not when goods are ready
Freight + clearance | 2-5 days | 4-6 weeks | Ocean transit, customs, inland delivery
TOTAL, approved tech pack to inventory | 8-14 weeks | 18-28 weeks | Assumes nothing unusual
Begin three to six months before your intended launch, and longer for a seasonal collection. Most startup brands miss their launch by 8-12 weeks because they start counting from the day they contacted a factory, not from the day design began.